## Manual Chart
GANTT CHART
| TASK NAME | START DATE | END DATE | DEPENDENT ON | PRIORITY | PERCENT COMPLETE | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1. Website
1.1. | Appoint a member(s) of the team | 15/10 | 15/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
1.2. | Decide upon the structure of the website | 15/10 | 15/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
1.3. | Create a simple website | 15/10 | 22/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
1.4. | Maintain the website | 15/10 | 24/11 | 1.3 | Medium | 100% | bar: WEEK 3 Th to WEEK 9 M
2. Requirements
2.1 | Appoint a member(s) of the team | 15/10 | 15/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
2.2. | Do a research, gather information | 15/10 | 22/10 | - | High | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
2.3. | Meet the customer and identify user requirements | 2020-12-10 | 15/10 | - | High | 100% | bar: WEEK 5 Th
2.4. | Identify functional and non-functional requirements | 15/10 | 22/10 | 2.3 | High | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
2.5. | Identify associated risks and decide upon alternatives | 22/10 | 29/10 | 2.4 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 4 Th to WEEK 5 Th
2.6. | Decide upon the presentation format | 29/10 | 29/10 | 2.5 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
2.7. | Add to the website | 29/10 | 29/10 | 2.6 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
2.8. | Maintain and update deliverable and website | 29/10 | 24/11 | 2.7 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th to WEEK 9 M
3. Architecture
3.1. | Appoint a member(s) of the team | 29/10 | 29/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
3.2. | Choose tools and the language | 29/10 | 29/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
3.3. | Design an abstract representation and construct diagrams | 29/10 | 2020-05-11 | 2.4 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th to WEEK 6 W
3.4. | Design a concrete representation and construct diagrams | 2020-05-11 | 19/11 | 3.3 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 6 Th to WEEK 8 W
3.5. | Justify the representation | 19/11 | 19/11 | 3.4 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
3.6. | Relate the concrete architecture to the requirements | 19/11 | 19/11 | 3.4 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
3.7. | Add to the website | 19/11 | 19/11 | 3.6 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
3.8. | Maintain and update deliverable and website | 19/11 | 24/11 | 3.7 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th to WEEK 9 M
4. Method selection and planning
4.1. | Appoint a member(s) of the team | 15/10 | 15/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
4.2. | Choose a development methodology | 15/10 | 15/10 | - | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
4.3. | Choose development and collaboration tools | 15/10 | 15/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th
4.4. | Justify the fitness of the chosen tools and identify alternatives | 15/10 | 22/10 | 4.3 | Medium | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
4.5. | Decide upon the team’s organization and justify | 15/10 | 22/10 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
4.6. | Make a project plan | 15/10 | 22/10 | - | High | 100% | bar: WEEK 3 Th to WEEK 4 W; WEEK 5 Th
4.7. | Provide weekly snapshots | 2020-12-11 | 19/11 | - | Low | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 7 Th to WEEK 8 W
4.8. | Discuss the evolution of the plan | 19/11 | 19/11 | 4.6 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
4.9. | Add to the website | 19/11 | 19/11 | 4.8 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
4.10. | Maintain and update deliverable and website | 19/11 | 24/11 | 4.9 | Meredith | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th to WEEK 9 M
5. Risk assessment and mitigation
5.1. | Appoint a member(s) of the team | 2020-05-11 | 2020-05-11 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 6 Th
5.2. | Do a research, gather information | 2020-05-11 | 2020-12-11 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 6 Th to WEEK 7 W
5.3. | Identify possible risks, their likelihood, severity and mitigation | 2020-05-11 | 2020-12-11 | 2.4, 4.6 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 6 Th to WEEK 7 W
5.4. | Justify the chosen format of presentation | 2020-12-11 | 19/11 | 5.3 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 7 Th to WEEK 8 W
5.5. | Give a tabular representation | 2020-12-11 | 19/11 | 5.3 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 7 Th to WEEK 8 W
5.6. | Add to the website | 19/11 | 19/11 | 5.5 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
5.7. | Maintain and update deliverable and website | 19/11 | 24/11 | 5.6 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th to WEEK 9 M
6. Implementation
6.1. | Do a research, gather information | 15/10 | 2020-12-11 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 7 W
6.2. | Decide upon the game design (graphics, music) | 15/10 | 2020-12-11 | - | Medium | 100% | bar: WEEK 3 Th to WEEK 7 W
6.3. | Write the code of the game | 2020-05-11 | 22/11 | 2.4,3.3,3.4 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 6 Th to WEEK 8 Th
6.4. | Identify unimplemented features | 22/11 | 22/11 | 6.3 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
6.5. | Add screenshots to the website | 22/11 | 22/11 | 6.3 | Low | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th
6.6. | Provide an executable JAR of the game and a zip file with the code | 22/11 | 24/11 | 6.3 | Medium | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 8 Th to WEEK 9 M
7. Assessment
7. | Submit our website URL and a zipfile with all deliverables | 24/11 | 24/11 | 6.6 | High | 100% | bar: WEEK 3 Th to WEEK 3 F; WEEK 5 Th; WEEK 9 T